## Summary
Project: E-commerce Website |  |  |  |  | Start Date: June 1, 2026 |  |  |  |  | Status: Completed
QA Lead: Mariel Balba |  |  |  |  | Target End Date: June 12, 2026 |  |  |  |  | Signoff Build: 1.2.1
[5 empty] | Actual End Date: June 10, 2026 |  |  |  |  | Jira Dashboard: link
Dashboard
Test Case Summary By Category | [5 empty] | Test Case Summary By Priority
Category | Total | In Progress | Passed | Failed | Completion | Priority | Total | In Progress | Passed | Failed | Completion
Functional | 19 | 0 | 18 | 1 | 100% | High | 14 | 0 | 13 | 1 | 100%
Non-functional | 7 | 0 | 7 | 0 | 100% | Medium | 2 | 0 | 2 | 0 | 100%
[6 empty] | Low | 1 | 0 | 1 | 0 | 100%
Overall | 26 | 0 | 25 | 1 | 100%
[6 empty] | Overall | 17 | 0 | 16 | 1 | 100%

## Test Case
Functional
Test Case ID | Title | Module / Feature | Priority | Preconditions | Test Steps | Expected Result | Status | Remarks | Bug Link
TC-F-01 | Verify user can access Login page | Login button | High | 1. User is on any page except Login page | 1. Click login button in navigation bar | 1. Login page loads successfully | Passed
TC-F-02 | Verify user can login with valid credentials | Login form | High | 1. User is on Login page 2. User has existing account | 1. Input valid login credentials 2. Click login button | 1. User is successfully logged in | Passed
TC-F-03 | Verify user cannot login with empty/invalid credentials | Login form | High | 1. User is on Login page | 1. Input invalid/empty credentials 2. Click login button | 1. Error message is displayed 2. User cannot login | Passed
TC-F-04 | Verify user can access Reset password page | Login form | High | 1. User is on Login page 2. User has existing account | 1. Click “Forgot your password?” link | 1. Reset password page loads successfully | Failed
TC-F-05 | Verify user can navigate to Sign up page from login form | Login form | Low | 1. User is on Login page | 1. Click “Sign up” | 1. Sign up page loads successfully | Passed
TC-F-06 | Verify user can access Cart page | Cart page | High | 1. User is on any page except Cart page | 1. Click cart button in navigation bar | 1. Cart page loads successfully | Passed
TC-F-07 | Verify empty cart page displays correct message | Cart page | High | 1. No product is added to cart | 1. Navigate to Cart page | 1. Message “Your cart is empty” is displayed | Passed
TC-F-08 | Verify "Start Shopping" button is visible and clickable | Cart page | Medium | 1. User is on Cart page 2. Cart is empty | 1. Observe and click “Start Shopping” button | 1. “Start Shopping” button is visible 2. User is redirected to shop page | Passed
TC-F-09 | Verify product details are displayed correctly | Cart page | High | 1. User is on Cart page 2. Cart has at least 1 product | 1. Observe product name, description, and price | 1. Displays correct product name, description, and price | Passed
TC-F-10 | Verify user can increase and decrease quantity of the product | Cart page | High | 1. User is on Cart page 2. Cart contains product with default quantity = 1 | 1. Click “+” and “–” buttons | 1. Quantity updates correctly 2. Subtotal, free shipping treshold, and Total recalculates | Passed
TC-F-11 | Verify cart icon shows correct item count | Cart icon | Medium | 1. User is on Cart page 2. Cart contains products | 1. Check cart badge count | 1. Cart icon displays total number of items in cart | Passed
TC-F-12 | Verify system prevents quantity below 1 | Cart page | High | 1. User is on Cart page 2. Cart contains product with default quantity = 1 | 1. Attempt to decrement below 1 | 1. System prevents quantity <1, disabled button state shown | Passed
TC-F-13 | Verify user can remove product from cart | Cart page | High | 1. User is on Cart page 2. Cart contains product | 1. Click trash icon | 1. Product is removed from cart 2. Cart badge scount updates | Passed
TC-F-14 | Verify order summary subtotal calculation | Cart page | High | 1. User is on Cart page 2. Cart contains product | 1. Observe subtotal amount | 1. Subtotal computation is correct | Passed
TC-F-15 | Verify shipping cost is displayed correctly | Cart page | High | 1. User is on Cart page 2. Cart contains product | 1. Observe shipping cost | 1. Shipping cost is correct | Passed
TC-F-16 | Verify shipping threshold is displayed correctly | Cart page | High | 1. User is on Cart page 2. Subtotal is less than $50 | 1. Observe shipping threshold display | 1. Shows remaining amount needed for free shipping | Passed
TC-F-17 | Verify cart applies free shipping when subtotal reaches $50 | Cart page | High | 1. User is on Cart page 2. Subtotal is $50 or more | 1. Observe shipping amount and threshold display | 1. Shipping becomes free 2. Free shipping threshold display diappears | Passed
TC-F-18 | Verify total calculation | Cart page | High | 1. User is on Cart page 2. Cart contains product | 1. Observe total amount | 1. Total amount calculation is correct | Passed
TC-F-19 | Verify “Continue Shopping” button redirects to Shop page | Cart page | Medium | 1. User is on Cart page 2. Cart contains product | 1. Click “Continue Shopping” button | 1. User redirected to Shop page | Passed
TC-F-20 | Verify “Proceed to Checkout” button redirects to Checkout page | Cart page | High | 1. User is on Cart page 2. Cart contains product | 1. Observe and click "Proceed to Checkout" button | 1. Button is visible 2. User is redirected to Checkout page | Passed
Non-Functional
ID | Title | Module / Feature | Priority | Preconditions | Test Steps | Expected Result | Status | Remarks
TC‑NF‑01 | Verify Login page loads within 3 seconds | Login page | High | 1. User is on any page other than Login page | 1. Navigate to Login page | 1. Page loads within 3 seconds | Passed
TC‑NF‑02 | Verify Login page renders consistently across browsers | Login page | Medium | N/A | 1. Open Login page in Chrome, Edge, Firefox | 1. Page renders consistently | Passed
TC‑NF‑03 | Verify system prevents SQL injection in login fields | Login page | High | 1. User is on Login page | 1. Enter ' OR '1'='1 in email field 2. Enter random password 3. Click “Login” | 1. System prevents injection and shows error | Passed
TC‑NF‑04 | Verify Login page supports screen reader accessibility | Login page | Medium | 1. Screen reader is enabled | 1. Navigate to Login page 2. Use screen reader | 1. Labels “Email” and “Password” are read aloud correctly | Passed
TC‑NF‑05 | Verify Cart page loads within 3 seconds | Cart page | High | 1. User is on any page other than Cart page | 1. Navigate to Cart page | 1. Page loads within 3 seconds | Passed
TC‑NF‑06 | Verify Cart page renders consistently across browsers | Cart page | Medium | N/A | 1. Open Login page in Chrome, Edge, Firefox | 1. Page renders consistently | Passed
TC‑NF‑07 | Verify Cart page supports screen reader accessibility | Cart page | Medium | 1. Screen reader is enabled | 1. Navigate to Login page 2. Use screen reader | 1. Product names, prices, and order summary are read aloud correctly | Passed